## Sheet1
| SwearWolves | Abigail | Logan | Quinton
Week 1 | Teams
Week 2 | Github
Week 3 | Conceptualize | Art design | Coding | Research
Week 4 | Planning
Week 5 | Define core mechanics of the game
Week 6 | Implement core mechanics |  |  | Menus
Week 7
Week 8 | Player design | Implementing visuals |  | SFX
Week 9 | Enemy design/mechanics
Week 10
Week 11 | Fancying up
Week 12 | Integration/testing
Week 13
Week 14 | Balance
Week 15 | Deliver Project